## Guidance
Introduction
This template has been introduced to provide a common format by which the relevant actions from the annual service plan for an individual service area can be recorded.
The service action plan should identify all actions that contribute to delivering the Corporate Plan. These should be specific projects, implementation of new legislation and actions to improve service delivery and performance (arising from value for money service reviews, assurance statements, risk mitigation etc). At the present time, the service action plan should not include any actions that relate to “day to day” work. For example, attendance at committee meetings or working groups.
Actions must be linked directly into the corporate business planning process, to ensure that there is sufficient budget to deliver the intended programme of work.
Service action plans are prepared annually, although service areas will be considering five-year budgetary implications. All Heads of Service should communicate with other service areas to ensure that any cross-cutting issues are picked up. Heads of Service should ensure that these cross-cutting issues are included in other contributors' service action plans and that other contributors are aware of the timings.
Completion of the Template
The service action plan should be completed in draft format by the 1 April 2017 and placed on the g:drive under the relevant service name.
The template is an Excel spreadsheet. It should be completed following the guidelines set out below.
ACTION TITLE
This should be the short title of the project / main action, which may consist of a number of sub-actions. The Action Title should be limited to approximately 10 words. A project or action is a task or activity, or a series of tasks or activities, which can be allocated to individuals and is time constrained, with a defined beginning and end.
OBJECTIVE
There is a drop-down menu on the Excel spreadsheet listing the relevant objectives. One of the three objectives should be selected: - Attractive & Thriving - Prosper & Protect - Responsive & Efficient
DESCRIPTION OF THE ACTION
The full description of the Action Title, where extra details can be added and acronyms can be written in full, if required.
DESIRED OUTCOME
Details of the anticipated outcome that will be achieved following delivery of the project / main action, including the timescale for realisation. The outcome should prove specifically that the service area achieved what it was aiming to achieve when the project / main action was initially authorised. If applicable, details of any relevant measures of success should be set out, including baseline and target figures and expected achievement dates.
SUB-ACTION
Sub-actions can be used to break down the project / main action into its constituent parts, setting out the specific activities that need to be completed in order to complete the project / main action.
MILESTONES
Milestones must be used to either break down each project / main action into its constituent parts or if used, to break down each sub-action into its constituent parts. By splitting an action into discrete tasks, it helps service areas to plan the required work and monitor progress.
DATES
A Planned Start Date and Due Date are required for each milestone.
The earliest milestone Planned Start Date will be the Planned Start Date of the associated sub-action. The latest milestone Due Date will be the Due Date of the associated sub-action. Likewise, the earliest sub-action Planned Start Date will be the Planned Start Date of the associated project / main action and the latest sub-action Due Date will be the Due Date of the associated project / main action.
PLANNED START DATE
A Planned Start Date is the date on which a milestone is due to start. Format - DD/MM/YY (e.g. 01/04/17)
DUE DATE
A Due Date is the date on which a milestone is due to be completed. Format - DD/MM/YY (e.g. 31/03/18)
ASSIGNED TO
The Assigned To field should identify the officer who is responsible for delivering a project / main action or sub-action. It should be completed for each project / main action or if used, it should be completed for each sub-action. Typically, this will be an officer at service manager level. The officer's name should be used (e.g. John Smith) rather than their job title.
MANAGED BY
The Managed By field should identify the officer who has overall responsibility for managing a project / main action or sub-action. This is likely to be the officer who has overall responsibility for managing the project / main action. Typically, this will be an officer at head of service level. The officer's name should be used (e.g. John Smith) rather than their job title.
WHAT LEARNING & DEVELOPMENT IS REQUIRED?
Details of any learning and development that is required to complete the relevant activities or achieve the desired outcome. It is important that these details be provided, as it will help the Council's Investors in People re-accreditation.
Colour Coding Projects / Main Actions (Optional)
Colour codes can be used to show the main driver for change. There are nine options to choose from, although service areas can tailor the options and colours to suit their particular requirements. Colour coding can help service areas to communicate the main driver behind each project / main action and can help put the service action plan into context.
Further Assistance
For further information or assistance on the completion of service action plans, please contact Rachel Cooper, Controls, Performance & Risk Manager (extension number 4606) or Tim Everitt, Performance Improvement Officer (extension number 4646).

## Template for Completion
Service Action Plan
Finance, Performance and Asset Management
Action | Corporate Objective | Target/Aim/Outcome | Planned Start Date | Due Date | Assigned to | Other services required (only list those service inputs which would not be considered 'business as usual')
2018/19
Accounts early closure | Responsive & Efficient | Complete statement of accounts by 31st May, and repond efficinetly to audit queries to allow their work to be completed by mid July | 2018-04-01 | 2018-07-31 | Antonio Ciampa
Integra Northgate interfaces functioing | Responsive & Efficient | Elimiates manual processing | 2018-04-01 | 2018-07-31 | Rachel Cooper | IT/ Revs and Bens
Development of E-forms | Responsive & Efficient | Reduces data entry and duplication | 2018-04-01 | 2019-03-31 | Rachel Cooper | IT/ MSU
Mobile approvals of Purchase Ordering | Responsive & Efficient | Allows more efficient working | 2018-04-01 | 2019-03-31 | Rachel Cooper | IT
Implement new Estates management software | Responsive & Efficient | Cost reductions, better reporting | 2018-04-01 | 2018-09-30 | David Charlton | IT/ MSU
Statutory service review | Responsive & Efficient | Enables the identification of savings opportunities that supports the setting of a balanced budget | 2018-04-01 | 2019-02-07 | Ian Couper | All
Disposal of surplus assets | Responsive & Efficient | Remove maintenance obligation and generate capital receipts | 2018-04-01 | 2019-03-31 | David Charlton | Legal, Planning?
Implement the new property compliance contract | Responsive & Efficient | Contract in place, working effectively to deliver property compliance and efficient contracting of other works | 2018-04-01 | 2018-12-31 | Michael Clark
Develop a new helpdesk for Property Services | Responsive & Efficient | Efficinet reporting and management of work requests | 2018-04-01 | 2019-03-31 | Michael Clark | IT
Produce Capital Strategy | Responsive & Efficient | Compliance with legislation, management of risk | 2018-04-01 | 2019-02-07 | Antonio Ciampa
2019/20
Disposal of surplus assets | Responsive & Efficient | Remove maintenance obligation and generate capital receipts | 2019-04-01 | 2020-03-31 | David Charlton | Legal, Planning
Respond to consultations and determine the impact of any changes in Local Government funding mechanisms | Responsive & Efficient | To try and get the best funding outcomes for the Council, and determine the impacts | 2018-04-01 | 2020-03-31 | Antonio Ciampa
2020/21 and 2021/22
Disposal of surplus assets | Responsive & Efficient | Remove maintenance obligation and generate capital receipts | 2018-04-01 | 2019-03-31 | David Charlton | Legal, Planning
Note on B3: Use the drop-down menu to select the relevant objective for the action. There are three objectives to choose from: Attractive & Thriving Prosper & Protect Responsive & Efficient You should be able to relate each action back to one of these objectives.
Note on D3: Format - DD/MM/YY
Note on E3: Format - DD/MM/YY

## Completed Example
2018/19 Service Action Plan (Completed Example)
Action | Corporate Objective | Target/Aim/Outcome | Planned Start Date | Due Date | Assigned To | Other services required
Preparing and submitting a Local Plan which passes inspection and establishes areas in which sustainable development may take place in future | Prosper & Protect | The publication of a revised timetable (Local Development Scheme) for the preparation of a Local Plan (Corporate Plan)to set a level of housing growth (including affordable housing) while considering the need to preserve all that is good about our area. | 2018-04-01 | 2019-03-31 | Louise Symes